## Plant Monitoring Sensor Network
Project Dashboard - Comprehensive Project Tracking System
M. Zaeem ¦ Electronics & Embedded Systems Engineer ¦ BSc Electrical Engineering ¦ MSc Autonomous Systems
1. Project Basic Information
Project Name: | Plant Monitoring Sensor Network
Client Name: | John bambery
Start Date: | 2025-10-25 |  | Expected End Date: | 2025-11-30
Pricing Model: | Fixed Price | Hourly Rate
Hourly Rate Per Hour ($): | 20.87 |  | Total Project Budget: |  | 5000$
Payment by Milestone:
2. Project Requirements
Project Requirements: The project involves designing and building an MVP prototype of a multi-modal plant monitoring system. It includes two battery-powered, weatherproof sensor nodes integrating environmental sensors (soil moisture, temperature, humidity, light, pH, atmospheric pressure) and plant communication sensors (bioelectric potential, VOCs, IR leaf temperature, optional ultrasonic). Each node must support data collection, logging, and LoRa transmission, with firmware for sensor calibration, power management, and basic visualization.
3. Project Milestones | Start Date:
Milestone 1 | Task Requirements |  | Hours Spent | Description | Status
| Finalize System Architecture |  | 12 | Planning & Initial Testing | Complete
| Finalising Components and Create Shopping List |  | 26 |  | Complete
Breadboard testing with Sensors (solderless)
Firmware Development with sensor interation
Real-World Unit Testing (Minimal Functionalities ofline Version)
Integrate battery & solar backup
| Milestone 1 Hours : |  | 38
Milestone 2 | Task Requirements |  | Hours Spent | Description | Status
| Add LoRa & IoT functionality |  |  | Power & Connectivity (IoT or LORA)
Develop central node / desktop backend for data preprocessing
Assemble waterproof enclosure & place sensors
Firmware enhancement (calibration, buffering, power management)
PCB assembly & solder components (Adding Indicators on Enclosure)
| Milestone 2 Hours : |  | 0
Milestone 3 | Task Requirements |  | Hours Spent | Description | Status
| System integration (hardware + firmware + sensors) |  |  | Final Assembly & Delivery
End-to-end testing (sensors, battery, LoRa, visualization)
Complete documentation (manuals, diagrams, instructions)
Complete manuals, diagrams, and assembly instructions.
Deliver final project to client
| Milestone 3 Hours : |  | 0
4. Key Deliverables |  | Additional Requirements | Project End Goal and Approval Criteria
Sensor Selection |  | Hardware | All hardware components functioning to specification Software meets All requirements with no critical bugs Client signs off on final deliverables
Firmware Development |  | LoRa communication or WIFI
Schematic Drawing |  | Assembled sensor nodes
PCB Layout |  | Power requirements
Gerber Files |  | Solar battery system
Bill of Materials (BOM) |  | Software | Design
PCB Fabrication Ordering |  | Firmware sensor integration | IP67 weatherproof enclosure
PCB Assembly (soldering components) |  | Sensor calibration option | Outdoor mounting system and Compact modular design
Board Testing |  | LED status indicators | Corrosion-resistant materials
3D Enclosure Design
5. Unallocated Task Time Tracking
Task Description |  |  |  |  | Hours Spent
|  | Hours: |  |  | 0
6. Additional Expenses :
Item / Description | Category | Notes | Cost per Unit ($) | Units | Total ($)
PCB Fabrication (JLCPCB) | Fabrication |  |  |  | 0
Customs VAT | Customs/Tax |  |  |  | 0
Enclosure Printing | Outsourcing |  |  |  | 0
PCB Assembly | Assembly Service |  |  |  | 0
Components | Components LCSC |  |  |  | 0
Unit Testing Labor | Testing |  |  |  | 0
Delivery to Client | Logistics |  |  |  | 0
Others |  |  |  |  | 0
|  |  |  | Total Cost: | 0
7. Payment Section
Hourly Payments
Task / Milestone | Rate ($/hr) | Hours Worked | Amount ($) | Paid ($) | Remaining ($)
Milestone 1 | 20.87 | 38 | 793.06 | 500 | 293.06
Milestone 2 | 20.87 | 0 | 0 |  | 0
Milestone 3 | 20.87 | 0 | 0 |  | 0
Extra Tasks (Unallocated) | 20.87 | 0 | 0 |  | 0
Additional Expenses | Nil | Nil | 0 |  | 0
Total Amount: |  | 38 | 793.06 | 500 | 293.06
Thank you for choosing to work with me. I truly appreciate your trust, and I’ll do my best to bring your idea to life with precision, dedication, and transparency. This spreadsheet has been created to provide a clear overview of project scope, progress, and costs, ensuring full visibility at every step. Please Note: The quotation provided does not include external expenses such as: - Component sourcing (AliExpress, Digi-Key, etc.) - PCB fabrication or assembly services (e.g., JLCPCB, PCBWay) - Import duties, VAT, or customs clearance fees - Packaging or shipping of prototypes - Specialized tooling or any outsourced service costs - These costs will be discussed and billed separately if required during the project. Looking forward to building something great together from concept to completion, I'm here as your technical partner. Warm regards, M. Zaeem Electronics & Embedded Systems Engineer

## Component List
Sr. No | Component Name | Variant | Description / Use | Link to Cart | Quantity | Unit Price | Total Price (Euro)
1 | LSM6DSO32 6-DOF Accelerometer Adafruit | 1528-4692-ND | Measures acceleration and rotation. | https://www.digikey.fi/short/0h7tf7fn | 1 | 10.65 | 10.65
2 | nRF52840 Module with Antenna | 672-NINA-B306-01BCT-ND | Bluetooth wireless module for for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 6.93 | 6.93
3 | BMP390 Precision Barometric Sensor Adafruit | 1528-4816-ND | Measures altitude via pressure. | https://www.digikey.fi/short/0h7tf7fn | 1 | 9.33 | 9.33
4 | Nano 33 BLE Rev2 Arduino | 1050-ABX00071-ND | Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 19.69 | 19.69
5 | Seeed Studio XIAO ESP32C3 | 1597-113991054-ND | Backup Option Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 4.25 | 4.25
|  |  | Aproximate Bill of Materials = |  |  |  | 50.85
Not shipped is red
Shipped is yellow
Arrived is green
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Additional Project Details
Additional Project Information
2