## Project Goal

The client wants a prototype multi-modal plant communication sensor system. The system must monitor environmental and plant-specific signals, transmit data wirelessly via LoRa, and be robust enough for outdoor use. The prototype will be a foundation for larger-scale deployments.

## Core Requirements

### 1. Hardware

#### Microcontroller

- ESP32-C3 board (built-in WiFi/Bluetooth)

- Must handle multiple sensors simultaneously

- Low power for battery operation

- Compatible with Arduino IDE or MicroPython

#### Wireless Communication

- LoRa module (SX1276 or equivalent)

- Frequency: 915 MHz

- Range: 2 km+

- Supports data transmission and ideally basic mesh networking

#### Power System

- Solar panel charging (20–50 W)

- Lithium battery (18650 or equivalent, ~7Ah)

- PWM charge controller with battery protection

- System should last 30+ days without sunlight

- Optimize power consumption for multiple sensors

#### Sensors

Environmental Sensors:

- Capacitive soil moisture (corrosion-resistant)

- DHT22 temperature/humidity

- Light intensity (PAR preferred)

- pH sensor

- Atmospheric pressure

Plant Communication Sensors:

- Electrical potential sensor (bioelectric signals)

- VOC (volatile organic compound) gas sensor

- IR leaf temperature (non-contact)

- Optional: Ultrasonic microphone (20–100 kHz)

Sampling and Accuracy:

- Sampling rates: 1 Hz – 1 kHz (depending on sensor)

- Accuracy: ±2% environmental, ±5% plant communication

- Local data storage for 30-day buffer

### 2. Software/Firmware

- Complete firmware for ESP32-C3

- Sensor integration and calibration routines

- LoRa data transmission

- Power management optimization

- Data logging and buffering

- Structured data packets with error checking

- Network management (initially star topology)

- Compatible with Arduino IDE or MicroPython

- Well-commented, documented code

### 3. Enclosure & Physical Design

- Weatherproof (IP67)

- Corrosion-resistant materials

- Proper ventilation for soil/air sensors

- Mountable outdoors (trees, posts)

- Maintenance access (battery replacement)

- Compact and modular design

- LED indicators for system status

### 4. Deliverables

#### Hardware Deliverables

- 1–2 fully assembled and tested sensor nodes

- All sensors properly integrated

- Solar + battery system functional

- LoRa communication tested

- Weatherproof enclosure

#### Software Deliverables

- ESP32-C3 firmware with sensor integrations

- Sensor calibration data and system parameters

- LoRa communication protocol implementation

- Basic documentation (code comments, user guide)

- Validation and test results

#### Documentation

- Component list and wiring diagrams

- Step-by-step assembly instructions

- User manual for operation

- Troubleshooting guide

### 5. Technical Challenges

- Multi-sensor integration: handling different sensor types and sampling rates, avoiding interference

- Plant signal processing: filtering bioelectric signals, calibrating VOC sensors, correlating data

- Power optimization: sleep/wake cycles, efficient energy use, solar/battery management

- Environmental durability: moisture/temperature protection, maintaining sensor accuracy

### 6. Project Timeline (6 weeks)

| Week | Tasks |
| --- | --- |
| 1 | Planning, component procurement, circuit design, software architecture |
| 2–3 | Hardware development, PCB or breadboard assembly, sensor integration, power system assembly, initial firmware |
| 4–5 | Complete firmware, sensor calibration, LoRa integration, system integration testing |
| 6 | Final assembly, weatherproofing, validation, documentation, handover |

### 7. Budget (USD $2,000–4,000)

- Electronics & Components: $800–1,200

- Enclosure & Mechanical: $300–500

- Development Time (hardware/software/testing): $800–2,000

- Contingency (replacements, shipping, modifications): $200–400

- Total: $2,100–4,100

### 8. Contractor Requirements

- Essential: ESP32/Arduino development, LoRa integration, solar/battery systems, weatherproof design, PCB preferred

- Preferred: Agri-tech or environmental monitoring experience, analog signal processing, plant sensor experience, mesh networks

- Communication: Fluent English, regular progress updates (2–3x/week), detailed documentation

### 9. Future Considerations

- Prototype must be scalable for manufacturing and large deployments (25+ nodes)

- Clean, modular code for reproducibility

- Work-for-hire: all IP and source code belongs to client

- Potential for ongoing projects and venture funding

### 10. Client Priorities

- Ready to start within 1 week

- Functional outdoor prototype

- Robust, reliable LoRa communication

- Accurate sensor readings

- Good documentation for replication and scaling

Target measurements:

- Total VOCs (broad-spectrum PID)

- Alcohols / Aldehydes / Benzenoids (semi-selective MOx)

- Amines / Sulfides (semi-selective MOx)

- NH₃ – Ammonia

- H₂S – Hydrogen sulfide

- C₂H₄ – Ethylene

- NO – Nitric oxide

- CH₄ – Methane

- CO – Carbon monoxide

- HCHO – Formaldehyde

- O₃ – Ozone

- Ethanol / Alcohol

### ✅ Already Covered (Done)

- Alcohol / Ethanol – SEN0376

- O₃ (Ozone) – SEN0472

- CH₄ (Methane) – SEN0654

- CO (Carbon Monoxide) – SEN0466

- NH₃ (Ammonia) – SEN0469

- H₂S (Hydrogen Sulfide) – SEN0467

### ⚙️ Not Yet Covered (Still Missing)

- Total VOCs (broad-spectrum PID)

- Alcohols / Aldehydes / Benzenoids (semi-selective MOx)

- Amines / Sulfides (semi-selective MOx)

- C₂H₄ (Ethylene)

- NO (Nitric Oxide)

- HCHO (Formaldehyde)