## Plant Monitoring Sensor Network
Project Dashboard - Comprehensive Project Tracking System
M. Zaeem ¦ Electronics & Embedded Systems Engineer ¦ BSc Electrical Engineering ¦ MSc Autonomous Systems
1. Project Basic Information
Project Name: | Plant Monitoring Sensor Network
Client Name: | John bambery
Start Date: | 2025-10-25 |  | Expected End Date: | 2026-02-28
Pricing Model: | Fixed Price | Hourly Rate
Hourly Rate Per Hour ($): | 20.87 |  | Total Project Budget: |  | 5000$
Payment by Milestone:
2. Project Requirements
Project Requirements: The project involves designing and building an MVP prototype of a multi-modal plant monitoring system. It includes two battery-powered, weatherproof sensor nodes integrating environmental sensors (soil moisture, temperature, humidity, light, pH, atmospheric pressure) and plant communication sensors (bioelectric potential, VOCs, IR leaf temperature, optional ultrasonic). Each node must support data collection, logging, and LoRa transmission, with firmware for sensor calibration, power management, and basic visualization.
3. Project Milestones | Start Date:
Milestone 1 – System Architecture, Hardware Development & Sensor Validation | Task Performed |  | Hours Spent | Description | Status
| 1. System Architecture Design • Designed the complete sensor network architecture. • Defined sensor roles, data flow, and communication protocol. • Finalized I2C-based inter-module communication. |  | 12 | Planning & Initial Testing | Complete
| 2. Sensor Research & Finalization • Researched and finalized 13 plant and environmental sensors. • Compared suppliers including Adafruit and DFRobot. • Coordinated with the client for technical validation. |  | 26 |  | Complete
| 3. Bill of Materials & Procurement • Prepared BOM covering all sensors and components. • Verified specifications, availability, and datasheets. • Coordinated payment and procurement from multiple vendors. • Received and verified all components. |  | 8 |  | Complete
| 4. Individual Sensor Testing & Firmware Development • Built breadboard prototypes and developed offline programs for each sensor. • Verified sensor data outputs and stability. • Resolved interfacing issues using datasheets and supplier documentation. • Confirmed reliability of individual sensors. |  | 10 |  | Complete
| 5. Mechanical Assembly & Enclosure Customization • Designed and customized enclosures. • Installed connectors, push buttons, and wiring pathways. • Performed soldering, wire routing, and structural adjustments. • Created detailed wiring diagrams. |  | 8 |  | Complete
| 6. Multi-Module Integration & I2C Network Debugging • Distributed 13 sensors across multiple modules. • Connected modules via I2C bus and resolved communication issues. • Troubleshot packet loss and inter-module data errors. • Validated stable multi-module data transmission. |  | 12 |  | Complete
| Milestone 1 Hours : |  | 76
Milestone 2-Power Optimization, Backend Development & Full System Integration | Task Performed |  | Hours Spent | Description | Status
| 1. Multi-Module Wiring Stabilization • Fixed wiring inconsistencies between sensor modules. • Improved I2C signal reliability over long cable runs. |  | 4 | Power & Connectivity (Backend and Frontend) | Complete
| 2. Power Optimization & Energy Management • Identified excessive battery drain due to high duty cycle operation. • Implemented deep sleep in firmware with optimized wake intervals. • Resolved data interruptions during deep sleep. • Validated stable battery-powered operation. |  | 14 |  | Complete
| 3. Backend Architecture & API Development • Designed backend system and using FastAPI. • Structured database schema for sensor data storage. • Implemented JSON-based data formatting. • Fixed data delivery and storage bugs. |  | 24 |  | Complete
| 4. Database & Data Integrity Management • Ensured proper logging of sensor values, device status, and timestamps. • Verified data persistence and consistency. |  | 7 |  | Complete
| 5. Frontend Web Dashboard Development • Designed web dashboard for real-time monitoring. • Integrated frontend with backend API and database for seamless data display. • Ensured accurate visualization of sensor data. |  | 22 |  | Complete
| 6. Full System Integration Testing • Integrated optimized firmware with backend and frontend. • Resolved deep sleep communication issues. • Verified sensor readings and data accuracy under real environmental conditions. • Conducted end-to-end system testing. |  | 12 |  | Complete
| Milestone 2 Hours : |  | 83
Milestone 3- Final Assembly, Protection, Documentation & Delivery | Task Performed |  | Hours Spent | Description | Status
| 1. Final Hardware Assembly • Completed structured wiring and module packaging. • Secured connections for field stability. |  | 6 | Final Assembly & Delivery | Complete
| 2. Waterproofing & Environmental Protection • Applied silicone sealing and protective enclosures. • Ensured durability for outdoor deployment. • Labeling the ports and the Modules. |  | 3 |  | Complete
| 3. Final Validation & Field Testing • Re-tested complete system after sealing. • Verified sensor accuracy, connectivity, and battery performance. |  | 5 |  | Complete
| 4. Packaging & Delivery Preparation • Prepared protective packaging for safe transportation. • Conducted final inspection of the complete system. |  | 2 |  | Complete
| 5. Documentation Preparation • Created schematic diagrams and final BOM. • Developed system architecture documentation and user manual. • Prepared setup and operational guidelines for the client. |  | 8 |  | Complete
| 6. Project Delivery • Delivered fully assembled, tested, and documented plant-based sensor network system via Fedex. |  | 1 |  | Complete
| Milestone 3 Hours : |  | 25
4. Key Deliverables |  | Additional Requirements | Project End Goal and Approval Criteria
Sensor Selection |  | Hardware | All hardware components functioning to specification Software meets All requirements with no critical bugs Client signs off on final deliverables
Firmware Development |  | LoRa communication or WIFI
Schematic Drawing |  | Assembled sensor nodes
PCB Layout |  | Power requirements
Gerber Files |  | Solar battery system
Bill of Materials (BOM) |  | Software | Design
PCB Fabrication Ordering |  | Firmware sensor integration | IP67 weatherproof enclosure
PCB Assembly (soldering components) |  | Sensor calibration option | Outdoor mounting system and Compact modular design
Board Testing |  | LED status indicators | Corrosion-resistant materials
3D Enclosure Design
6. Additional Expenses :
Item / Description | Category | Notes | Cost per Unit ($) | Units | Total ($)
Components, Hardware and Sensors | Components (Adafruit, Dfrobot Digilog, Mouser electronics) | Separate bill for sensors and purchased materials for the project, valued at 2,762 EUR, equivalent to 3,279.78 USD at the USD-to-EUR exchange rate of 1 EUR = 1.19 USD. | 3286 | 1 | 3286
Delivery to Client | Logistics | I haven’t received the invoice yet for FedEx International Economy (Tracking 888703177458). I will share it once the package is delivered and my card has been charged. This is what was shown when I placed the order for delivery. | 201.8 | 1 | 201.8
Received Amount | Amount details as mentioned in the Payment History section |  | 3465.12 | Remaining Balance: | 22.68
7. Received Payments History
Purpose | Date | Discription |  | Amount ($) | Paid ($)
Fiverr Order | 2025-11-08 | Recived order on Fiverr |  | 500 | 500
Project Components and Sensors | 2025-11-13 | Received 2,985 EUR for component purchasing, equivalent to 3,465.12 USD at the USD-to-EUR exchange rate of 0.86 on that day. |  | 3465.12 | 3465.12
Engineering and Manufacturing costs | 2025-12-04 | Received 1,249.51 EUR toward project engineering and manufacturing costs, equivalent to 1,452.92 USD at the USD-to-EUR exchange rate of 0.86 on the date received. |  | 1452.9 | 1452.9
Total Amount: |  | 0 |  | 5418.02 | 5418.02
8. Remaining Payments
Hourly Payments
Task / Milestone | Rate ($/hr) | Hours Worked | Amount ($) | Paid ($) | Remaining ($)
Milestone 1 | 20.87 | 76 | 1586.12 | 500 | 1086.12
Milestone 2 | 20.87 | 83 | 1732.21 | 1452.9 | 279.31
Milestone 3 | 20.87 | 25 | 521.75 |  | 521.75
Additional Expenses | Nil | Remaining payable for components and delivery. | 22.68 |  | 22.68
Total Amount: |  | 184 | 3862.76 | 1952.9 | 1909.86
Thank you for choosing to work with me. I truly appreciate your trust, and I did my best to bring your idea to life with precision, dedication, and transparency. With this stage complete, we will continue the Lora integration and work on one additional node. This spreadsheet provides a clear overview of project scope, progress, and costs, ensuring full visibility at every step. Please Note: - The document covers total project costs, including components, payments received, engineering and Mechanical work, prototype development, and delivery charges. - The hardware is already on the way and should arrive next week. - The remaining amount of $1,909 can be postponed until next month; a separate Upwork order can be created to process this payment or we will decide. Warm regards, M. Zaeem Electronics & Embedded Systems Engineer

## Component List
Sr. No | Component Name | Variant | Description / Use | Link to Cart | Quantity | Unit Price | Total Price (Euro)
1 | LSM6DSO32 6-DOF Accelerometer Adafruit | 1528-4692-ND | Measures acceleration and rotation. | https://www.digikey.fi/short/0h7tf7fn | 1 | 10.65 | 10.65
2 | nRF52840 Module with Antenna | 672-NINA-B306-01BCT-ND | Bluetooth wireless module for for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 6.93 | 6.93
3 | BMP390 Precision Barometric Sensor Adafruit | 1528-4816-ND | Measures altitude via pressure. | https://www.digikey.fi/short/0h7tf7fn | 1 | 9.33 | 9.33
4 | Nano 33 BLE Rev2 Arduino | 1050-ABX00071-ND | Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 19.69 | 19.69
5 | Seeed Studio XIAO ESP32C3 | 1597-113991054-ND | Backup Option Microcontroller for prototyping. | https://www.digikey.fi/short/0h7tf7fn | 1 | 4.25 | 4.25
|  |  | Aproximate Bill of Materials = |  |  |  | 50.85
Not shipped is red
Shipped is yellow
Arrived is green
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28

## Additional Project Details
Additional Project Information
2